## Ashish
		My Work Report

Sr.No.	Date	Project Name	Task	Assigned Details	Work Details	Issues	Solution	Document Details	Expected Time	Time Spent	Work Status	Other Details/ Remark

1	13/08/14	Task Management System	1. Create Reposetry On github to mentain the / Work details of every employee. / 2. Inform Team to use git hub and update each / and every action in this sheet and upload it on / Github so that it can be in Public Domain.	Assigned By / Tushar Sir. / (Mail details in case of emails coversion)	1.Created Reposetry On Local Host and shared it on Git Hub. / 2. Created A document Template to record the Work Details / And Uploaded in the Reposetry.	1. No Documentation of the work done.	1. Create Document on git hub so / that every one can share it and / Update their work details in one document.	This Is the Document / Of This Work.	Not Assigned		Working	To complete this task every team member / Should contribute and update their work / Details on github.
2	13/08/14	Task Management System	1.Prepare Document of Process To Use the / Github for Work-Report.	Assigned By / Tushar Sir.	1. Took screen shots and prepared documentation for the / github work-report.			Documentation On the Google Drive. / https://docs.google.com/a/aarogya.com/document/d/1oaxC_Hx5-AsBoxHzxSNs5BeInJWR4eRtFlIYELPIrlI/edit#	Not Assigned		Working	Will be complete today

## Pratap
		My Work Report

Sr.No.	Date	Project Name	Task	Assigned Details	Work Details	Issues	Solution	Document Details	Expected Time (Hr)	Time Spent	Work Status	Other Details/ Remark
	13/08/14	Github	Github configuaration on local machine	Ashish Dhavalikar	Downloading & installating github app for windows 8. / Creating clone repository on localhost. / Updating work report in clone	github app is not available. / Clone is not available	Downloading & installing github app. / Creating clone of work report repository by click on Clone in Desktop option in github dashboard.	No need	30Min	25Min	Completed	Download Github app for Windows 8/7 / https://windows.github.com/
			Updating work report	Pratap Shinde	Updating work report

## Sandeep
		My Work Report

Sr.No.	Date	Project Name	Task	Assigned Details	Work Details	Issues	Solution	Document Details	Expected Time	Time Spent	Work Status	Other Details/ Remark

## Parag
		My Work Report

Sr.No.	Date	Project Name	Task	Assigned Details	Work Details	Issues	Solution	Document Details	Expected Time	Time Spent	Work Status	Other Details/ Remark

## Pritam
		My Work Report

Sr.No.	Date	Project Name	Task	Assigned Details	Work Details	Issues	Solution	Document Details	Expected Time	Time Spent	Work Status	Other Details/ Remark

## Vrishali
		My Work Report

Sr.No.	Date	Project Name	Task	Assigned Details	Work Details	Issues	Solution	Document Details	Expected Time	Time Spent	Work Status	Other Details/ Remark
1	13/08/14	Task Management System	Create repository for daily work details.	Ashish	1.Clonned repository locallyby windows app / 2.Changes mage in repository. / 3.Commited changes. / 4.Synchronised them

## Sujit
		My Work Report

Sr.No.	Date	Project Name	Task	Assigned Details	Work Details	Issues	Solution	Document Details	Expected Time	Time Spent	Work Status	Other Details/ Remark

## Pundlik
		My Work Report

Sr.No.	Date	Project Name	Task	Assigned Details	Work Details	Issues	Solution	Document Details	Expected Time	Time Spent	Work Status	Other Details/ Remark

## Rahul
		My Work Report

Sr.No.	Date	Project Name	Task	Assigned Details	Work Details	Issues	Solution	Document Details	Expected Time	Time Spent	Work Status	Other Details/ Remark